## Start
FDG Construction Management Professional Toolkit
Edition | Philippines Edition / v1.0.0-rc.1
Use | Save a private copy before entering real project records.
1 Setup | Enter project ID, project name, as-of date and reporting interval in Setup.
2 Baseline | Enter unique WBS IDs, units, approved baseline quantities and weights totaling 100%.
3 Capture | Record Daily events once. Reported quantity and accepted quantity remain separate.
4 Review | Enter actual reviewer identity, evidence and dates. A selected status is not a signature.
5 Report | Report uses the selected interval; Dashboard uses the as-of date.
6 Control | Use the registers, Evidence and History. Preserve prior issued revisions.
Capacity | 200 rows per register (rows7-206). Extend ALL formulas, validation and ranges before more rows.
Input colors | Pale amber: editable. Pale green: calculated; do not overwrite.
Privacy | Public source contains blank templates and synthetic examples only. Keep client copies private.
Limits | Single-editor files. No automatic permission enforcement, conflict merging or legal certification.
Sample mode | BLANK TEMPLATE - no real project loaded
Help | Read IMPLEMENTATION_GUIDE.md in this release folder.

## Dashboard
Project management dashboard
Project | No project selected
As-of date
Accepted weighted progress | n.a.
Planned weighted progress | n.a.
Variance (percentage points) | n.a.
RFI overdue (not accepted/rejected) | n.a.
Open issues | 0
Open punch items | 0
Turnover pending acceptance | 0
WBS weight total | n.a.
Progress basis | Missing project, date or complete 100% weights
Evidence / quantity warnings | 0
Progress is evidence-based recorded quantity, not certification, billability or payment.

## Report
Period progress report
Project |  | Start |  | End
WBS ID | Activity | Unit | Reported in period | Accepted in period | Accepted to cutoff | Baseline quantity | Accepted fraction

## Setup
Project profile and report controls
Project ID
Project name
As-of date
Report start
Report end
Prepared by
Reviewed by
Issue revision
Review / issue state | Draft
Currency | PHP
Jurisdiction | Philippines; project and contract rules require review
Evidence custody

## WBS
Work breakdown and progress basis
Blank template - enter your approved project records
WBS ID | Project ID | Activity | Unit | Baseline Quantity | Weight | Planned Fraction | Accepted Events | Accepted Quantity | Accepted Fraction | Weighted Actual | Weighted Plan | Owner | Revision | Source Reference | Basis Check

## Daily
Daily site progress
Blank template - enter your approved project records
Event ID | Project ID | WBS ID | Event Date | Description | Unit | Reported Quantity | Accepted Quantity | Review State | Evidence Reference | Prepared By | Reviewer | Review Date | Revision | Source Reference | Evidence Check | Unit Check | Quantity Check

## Kickoff
Project startup and kickoff
Blank template - enter your approved project records
Item ID | Project ID | Item | Owner | Due Date | Status | Evidence Reference | Reviewer | Review Date | Revision | Source Reference

## RFI
Request for information register
Blank template - enter your approved project records
RFI ID | Project ID | WBS ID | Subject | Raised Date | Due Date | Owner | Status | Response Reference | Evidence Reference | Reviewer | Review Date | Revision | Source Reference | Next Action

## Submittals
Submittal register
Blank template - enter your approved project records
Submittal ID | Project ID | WBS ID | Document Title | Document Revision | Submitted Date | Due Date | Owner | Status | Response Reference | Evidence Reference | Reviewer | Review Date | Revision | Source Reference

## Issues
Issues, constraints and delays
Blank template - enter your approved project records
Issue ID | Project ID | WBS ID | Category | Description | Observed Date | Impact Basis | Owner | Due Date | Status | Next Action | Evidence Reference | Reviewer | Review Date | Revision | Source Reference

## QAQC
QA/QC status register
Blank template - enter your approved project records
Inspection ID | Project ID | WBS ID | Record Type | Description | Method Standard Reference | Acceptance Criterion | Observed Result | Inspection Date | Owner | Status | Evidence Reference | Reviewer | Review Date | Revision | Source Reference

## Changes
Variation and change register
Blank template - enter your approved project records
Change ID | Project ID | WBS ID | Description | Cause | Notice Date | Cost Impact PHP | Time Impact Days | Owner | Status | Authorization Reference | Evidence Reference | Reviewer | Review Date | Revision | Source Reference

## Billing
Progress billing evidence index
Blank template - enter your approved project records
Billing ID | Project ID | WBS ID | Description | Unit | Reported Quantity | Accepted Quantity | Billable Quantity | Billed Quantity | Paid Quantity | Unit Rate PHP | Billable Authority Reference | Billing Reference | Payment Reference | Evidence Reference | Owner | Revision | Source Reference

## Punch
Punch list
Blank template - enter your approved project records
Punch ID | Project ID | WBS ID | Location | Description | Responsible Trade | Owner | Due Date | Status | Closure Evidence Reference | Verified By | Verification Date | Revision | Source Reference

## Turnover
Turnover and closeout tracker
Blank template - enter your approved project records
Turnover ID | Project ID | WBS ID | Deliverable Type | Description | Responsibility Receiver | Owner | Due Date | Status | Blocking Issue Reference | Evidence Reference | Reviewer | Review Date | Revision | Source Reference

## Evidence
Evidence index
Blank template - enter your approved project records
Evidence ID | Project ID | Record Type | Origin | Locator | Captured Date | Captured By | Checksum | Access Class | Verification Status | Revision | Source Reference

## History
Revision and decision log
Blank template - enter your approved project records
History ID | Project ID | Target Record ID | Prior Revision | New Revision | Change Reason | Actor | Occurred Date | Decision Reference | Evidence Reference