## Start
FDG Construction Management Professional Toolkit
Edition | Philippines Edition / v1.0.0-rc.1
Use | Save a private copy before entering real project records.
1 Setup | Enter project ID, project name, as-of date and reporting interval in Setup.
2 Baseline | Enter unique WBS IDs, units, approved baseline quantities and weights totaling 100%.
3 Capture | Record Daily events once. Reported quantity and accepted quantity remain separate.
4 Review | Enter actual reviewer identity, evidence and dates. A selected status is not a signature.
5 Report | Report uses the selected interval; Dashboard uses the as-of date.
6 Control | Use the registers, Evidence and History. Preserve prior issued revisions.
Capacity | 200 rows per register (rows7-206). Extend ALL formulas, validation and ranges before more rows.
Input colors | Pale amber: editable. Pale green: calculated; do not overwrite.
Privacy | Public source contains blank templates and synthetic examples only. Keep client copies private.
Limits | Single-editor files. No automatic permission enforcement, conflict merging or legal certification.
Sample mode | SYNTHETIC EXAMPLE - not real work, payment or acceptance
Help | Read IMPLEMENTATION_GUIDE.md in this release folder.

## Dashboard
Project management dashboard
Project | DEMO-PH-001
As-of date | 2026-10-16
Accepted weighted progress | 35%
Planned weighted progress | 40%
Variance (percentage points) | -5%
RFI overdue (not accepted/rejected) | 1
Open issues | 1
Open punch items | 1
Turnover pending acceptance | 1
WBS weight total | 100%
Progress basis | Review data and approvals
Evidence / quantity warnings | 0
Progress is evidence-based recorded quantity, not certification, billability or payment.

## Report
Period progress report
Project | DEMO-PH-001 | Start | 2026-10-12 | End | 2026-10-16
WBS ID | Activity | Unit | Reported in period | Accepted in period | Accepted to cutoff | Baseline quantity | Accepted fraction
WBS-001 | Concrete slab | m3 | 50 | 45 | 45 | 100 | 45%
WBS-002 | Pipe installation | m | 60 | 40 | 40 | 200 | 20%

## Setup
Project profile and report controls
Project ID | DEMO-PH-001
Project name | Synthetic Cebu MEP Demonstration
As-of date | 2026-10-16T00:00:00.000Z
Report start | 2026-10-12T00:00:00.000Z
Report end | 2026-10-16T00:00:00.000Z
Prepared by | Demo Site Engineer
Reviewed by
Issue revision | 1
Review / issue state | Draft
Currency | PHP
Jurisdiction | Philippines; project and contract rules require review
Evidence custody

## WBS
Work breakdown and progress basis
SYNTHETIC EXAMPLE ONLY - replace with a separately saved blank workbook
WBS ID | Project ID | Activity | Unit | Baseline Quantity | Weight | Planned Fraction | Accepted Events | Accepted Quantity | Accepted Fraction | Weighted Actual | Weighted Plan | Owner | Revision | Source Reference | Basis Check
WBS-001 | DEMO-PH-001 | Concrete slab | m3 | 100 | 60% | 50% | 2 | 45 | 45% | 27% | 30% | Demo Site Engineer | 1 | DEMO-BASIS-001 | Valid
WBS-002 | DEMO-PH-001 | Pipe installation | m | 200 | 40% | 25% | 1 | 40 | 20% | 8% | 10% | Demo Site Engineer | 1 | DEMO-BASIS-002 | Valid

## Daily
Daily site progress
SYNTHETIC EXAMPLE ONLY - replace with a separately saved blank workbook
Event ID | Project ID | WBS ID | Event Date | Description | Unit | Reported Quantity | Accepted Quantity | Review State | Evidence Reference | Prepared By | Reviewer | Review Date | Revision | Source Reference | Evidence Check | Unit Check | Quantity Check
D-001 | DEMO-PH-001 | WBS-001 | 2026-10-12T00:00:00.000Z | Concrete placement | m3 | 20 | 20 | Accepted | E-001 | Demo Engineer | Demo Reviewer | 2026-10-13T00:00:00.000Z | 1 | DEMO-FIELD-001 | Recorded - verify authority | Matched | Recorded
D-002 | DEMO-PH-001 | WBS-001 | 2026-10-16T00:00:00.000Z | Concrete placement; quantity adjustment pending | m3 | 30 | 25 | Accepted | E-002 | Demo Engineer | Demo Reviewer | 2026-10-16T00:00:00.000Z | 1 | DEMO-FIELD-002 | Recorded - verify authority | Matched | Recorded
D-003 | DEMO-PH-001 | WBS-001 | 2026-10-17T00:00:00.000Z | Future-dated event excluded from cutoff | m3 | 50 | 50 | Accepted | E-003 | Demo Engineer | Demo Reviewer | 2026-10-17T00:00:00.000Z | 1 | DEMO-FIELD-003 | Recorded - verify authority | Matched | Recorded
D-004 | DEMO-PH-001 | WBS-002 | 2026-10-15T00:00:00.000Z | Pipe installation | m | 50 | 40 | Accepted | E-004 | Demo Engineer | Demo Reviewer | 2026-10-16T00:00:00.000Z | 1 | DEMO-FIELD-004 | Recorded - verify authority | Matched | Recorded
D-005 | DEMO-PH-001 | WBS-002 | 2026-10-16T00:00:00.000Z | Unreviewed field quantity | m | 10 |  | Submitted | E-005 | Demo Engineer |  |  | 1 | DEMO-FIELD-005 | Review pending | Matched | Not accepted

## Kickoff
Project startup and kickoff
SYNTHETIC EXAMPLE ONLY - replace with a separately saved blank workbook
Item ID | Project ID | Item | Owner | Due Date | Status | Evidence Reference | Reviewer | Review Date | Revision | Source Reference
K-001 | DEMO-PH-001 | Confirm reporting and approval matrix | Demo PM | 2026-10-10T00:00:00.000Z | Accepted | E-006 | Demo Reviewer | 2026-10-10T00:00:00.000Z | 1 | DEMO-MOM-001

## RFI
Request for information register
SYNTHETIC EXAMPLE ONLY - replace with a separately saved blank workbook
RFI ID | Project ID | WBS ID | Subject | Raised Date | Due Date | Owner | Status | Response Reference | Evidence Reference | Reviewer | Review Date | Revision | Source Reference | Next Action
RFI-001 | DEMO-PH-001 | WBS-002 | Confirm pipe route | 2026-10-10T00:00:00.000Z | 2026-10-14T00:00:00.000Z | Demo Coordinator | Submitted |  | E-007 |  |  | 1 | DEMO-DWG-001 | Obtain consultant response

## Submittals
Submittal register
SYNTHETIC EXAMPLE ONLY - replace with a separately saved blank workbook
Submittal ID | Project ID | WBS ID | Document Title | Document Revision | Submitted Date | Due Date | Owner | Status | Response Reference | Evidence Reference | Reviewer | Review Date | Revision | Source Reference
SUB-001 | DEMO-PH-001 | WBS-002 | Pipe material datasheet | A | 2026-10-12T00:00:00.000Z | 2026-10-20T00:00:00.000Z | Demo Coordinator | In Review |  | E-008 |  |  | 1 | DEMO-SPEC-001

## Issues
Issues, constraints and delays
SYNTHETIC EXAMPLE ONLY - replace with a separately saved blank workbook
Issue ID | Project ID | WBS ID | Category | Description | Observed Date | Impact Basis | Owner | Due Date | Status | Next Action | Evidence Reference | Reviewer | Review Date | Revision | Source Reference
ISS-001 | DEMO-PH-001 | WBS-002 | Constraint | Route clearance not confirmed | 2026-10-12T00:00:00.000Z | Linked RFI-001; schedule impact not yet evaluated | Demo PM | 2026-10-14T00:00:00.000Z | Open | Resolve RFI-001 | E-007 |  |  | 1 | DEMO-ISSUE-001

## QAQC
QA/QC status register
SYNTHETIC EXAMPLE ONLY - replace with a separately saved blank workbook
Inspection ID | Project ID | WBS ID | Record Type | Description | Method Standard Reference | Acceptance Criterion | Observed Result | Inspection Date | Owner | Status | Evidence Reference | Reviewer | Review Date | Revision | Source Reference
QC-001 | DEMO-PH-001 | WBS-001 | WIR | Slab placement observation | DEMO-ITP-001 | Project-specific criterion pending qualified review | Example observation only | 2026-10-16T00:00:00.000Z | Demo QA Engineer | In Review | E-002 |  |  | 1 | DEMO-WIR-001

## Changes
Variation and change register
SYNTHETIC EXAMPLE ONLY - replace with a separately saved blank workbook
Change ID | Project ID | WBS ID | Description | Cause | Notice Date | Cost Impact PHP | Time Impact Days | Owner | Status | Authorization Reference | Evidence Reference | Reviewer | Review Date | Revision | Source Reference
CHG-001 | DEMO-PH-001 | WBS-002 | Potential reroute | RFI response pending | 2026-10-16T00:00:00.000Z |  |  | Demo QS | Draft |  | E-007 |  |  | 1 | DEMO-CHANGE-001

## Billing
Progress billing evidence index
SYNTHETIC EXAMPLE ONLY - replace with a separately saved blank workbook
Billing ID | Project ID | WBS ID | Description | Unit | Reported Quantity | Accepted Quantity | Billable Quantity | Billed Quantity | Paid Quantity | Unit Rate PHP | Billable Authority Reference | Billing Reference | Payment Reference | Evidence Reference | Owner | Revision | Source Reference
BIL-001 | DEMO-PH-001 | WBS-001 | Example evidence index | m3 | 50 | 45 |  |  |  | 1000 |  |  |  | E-001; E-002 | Demo QS | 1 | DEMO-BILL-001

## Punch
Punch list
SYNTHETIC EXAMPLE ONLY - replace with a separately saved blank workbook
Punch ID | Project ID | WBS ID | Location | Description | Responsible Trade | Owner | Due Date | Status | Closure Evidence Reference | Verified By | Verification Date | Revision | Source Reference
P-001 | DEMO-PH-001 | WBS-002 | Zone A | Complete identification tags | Mechanical | Demo Supervisor | 2026-10-22T00:00:00.000Z | Open |  |  |  | 1 | DEMO-PUNCH-001

## Turnover
Turnover and closeout tracker
SYNTHETIC EXAMPLE ONLY - replace with a separately saved blank workbook
Turnover ID | Project ID | WBS ID | Deliverable Type | Description | Responsibility Receiver | Owner | Due Date | Status | Blocking Issue Reference | Evidence Reference | Reviewer | Review Date | Revision | Source Reference
T-001 | DEMO-PH-001 | WBS-002 | O&M manual | Submit approved O&M record | Demo Facility Manager | Demo Doc Controller | 2026-10-25T00:00:00.000Z | Pending | ISS-001 |  |  |  | 1 | DEMO-TURN-001

## Evidence
Evidence index
SYNTHETIC EXAMPLE ONLY - replace with a separately saved blank workbook
Evidence ID | Project ID | Record Type | Origin | Locator | Captured Date | Captured By | Checksum | Access Class | Verification Status | Revision | Source Reference
E-001 | DEMO-PH-001 | Synthetic fixture | FDG worked example | DEMO-ONLY/no-real-file | 2026-10-16T00:00:00.000Z | Demo Author |  | Public synthetic | Illustrative - not real evidence | 1 | FDG-CMT-SAMPLE
E-002 | DEMO-PH-001 | Synthetic fixture | FDG worked example | DEMO-ONLY/no-real-file | 2026-10-16T00:00:00.000Z | Demo Author |  | Public synthetic | Illustrative - not real evidence | 1 | FDG-CMT-SAMPLE
E-003 | DEMO-PH-001 | Synthetic fixture | FDG worked example | DEMO-ONLY/no-real-file | 2026-10-16T00:00:00.000Z | Demo Author |  | Public synthetic | Illustrative - not real evidence | 1 | FDG-CMT-SAMPLE
E-004 | DEMO-PH-001 | Synthetic fixture | FDG worked example | DEMO-ONLY/no-real-file | 2026-10-16T00:00:00.000Z | Demo Author |  | Public synthetic | Illustrative - not real evidence | 1 | FDG-CMT-SAMPLE
E-005 | DEMO-PH-001 | Synthetic fixture | FDG worked example | DEMO-ONLY/no-real-file | 2026-10-16T00:00:00.000Z | Demo Author |  | Public synthetic | Illustrative - not real evidence | 1 | FDG-CMT-SAMPLE
E-006 | DEMO-PH-001 | Synthetic fixture | FDG worked example | DEMO-ONLY/no-real-file | 2026-10-16T00:00:00.000Z | Demo Author |  | Public synthetic | Illustrative - not real evidence | 1 | FDG-CMT-SAMPLE
E-007 | DEMO-PH-001 | Synthetic fixture | FDG worked example | DEMO-ONLY/no-real-file | 2026-10-16T00:00:00.000Z | Demo Author |  | Public synthetic | Illustrative - not real evidence | 1 | FDG-CMT-SAMPLE
E-008 | DEMO-PH-001 | Synthetic fixture | FDG worked example | DEMO-ONLY/no-real-file | 2026-10-16T00:00:00.000Z | Demo Author |  | Public synthetic | Illustrative - not real evidence | 1 | FDG-CMT-SAMPLE

## History
Revision and decision log
SYNTHETIC EXAMPLE ONLY - replace with a separately saved blank workbook
History ID | Project ID | Target Record ID | Prior Revision | New Revision | Change Reason | Actor | Occurred Date | Decision Reference | Evidence Reference
H-001 | DEMO-PH-001 | D-002 | 0 | 1 | Synthetic example prepared | Demo Author | 2026-10-16T00:00:00.000Z | DEMO-DECISION-001 | E-002